## Sheet1
Task # | Task | Status | User Story | Epic | Scope Category | Epic # | Epic | User Story
1 | Log bug for the javascript messages | Done | Article Management | 1 | Bugs | 1 | Create a Blog Website App to allow users to locate, display, like and comment on articles about Django | Account creation
2 | Add new JS file & try to get working | Done | Article Management | 1 | Bugs |  |  | Article Management
3 | Revert to old code if need to trigger the error | Done | Article Management | 1 | Bugs |  |  | Article Drafting
4 | Explain how new code solves the error | Done | Article Management | 1 | Bugs |  |  | Approve comments
5 | Add to Kanban as bug #2 | Done | Article Management | 1 | Bugs |  |  | Article Organisation
6 | Add to Bugs readme as bug#2 | Done | Article Management | 1 | Bugs |  |  | View articles listing
7 | Update testing section for that code | Done | Article Management | 1 | Testing |  |  | View Likes
8 | Add bug for not using jinja syntax | Done | Article Management | 1 | Bugs |  |  | Open an article
9 | Change red hover to green | Done | View articles listing | 1 | UX |  |  | View article comments
10 | Change light blue article author tags to match color scheme | Done | View articles listing | 1 | UX |  |  | Comment on an article
11 | Change buttons on signin page to be black | Done | View articles listing | 1 | UX |  |  | Like / Unlike
12 | Make boxes smaller on home page & polls page etc | Done | View articles listing | 1 | UX |  |  | Add a like to an article
13 | Code Validation | Done | All User Stories | All | Code validation |  |  | Remove a like from an Article
14 | HTML validation W3C | Done | All User Stories | All | Code validation | 2 | Create a Poll App to allow users to express their preference and opinions on topics relevant to the Website App content | View current voting results of an opinion poll question
15 | CSS validation Jigsaw | Done | All User Stories | All | Code validation |  |  | View a list of the site's opinion poll questions
16 | Javascript Validation Jshint | Done | All User Stories | All | Code validation |  |  | Vote my own preference to an opinion poll question
17 | Python validation PEP8 | Done | All User Stories | All | Code validation |  |  | View a list of the opinion poll question answer choices
18 | Combine back into one document, but have Testing & Features separate | Done | All User Stories | All | Readme update
19 | Local Deployment | Done | All User Stories | All | Deployment
20 | See note - pip3 install -r requirements.txt | Done | All User Stories | All | Deployment | Note: Ensure at all times throughout development that should-have prioritised user stories should not be more of the timebox user story points total
21 | Install local packages | Done | All User Stories | All | Deployment
22 | Create env.py file + which values | Done | All User Stories | All | Deployment
23 | Deployment | Done | All User Stories | All | Deployment
24 | General Deployment | Done | All User Stories | All | Deployment
25 | Remove references to Fantasy Football Centre | Done | All User Stories | All | Renaming
26 | Add screenshots for 27x manual tests | Done | All User Stories | All | Testing
27 | Amiresponsive | Done | All User Stories | All | UX
28 | Responsiveness on mobile – home page & polls page | Done | Article Organisation | 1 | UX
29 | Remove CI default image & replace with Dan image | Done | Article Organisation | 1 | Features
30 | Add to Tests | Done | Article Organisation | 1 | Testing
31 | Add to features | Done | Article Organisation | 1 | Features
32 | Pexels picture accreditations | Done | Article Organisation | 1 | Credits
33 | Change id to class for “home-page-container” | Done | View a list of the site's opinion poll questions | 2 | UX
34 | Favicon | Done | All User Stories | All | UX
35 | Add bug – will only display on home page, not others? | Done | All User Stories | All | Bugs
36 | Update tests to include login required mixin (tutor support) | Done | View a list of the site's opinion poll questions | 2 | Testing
37 | Add as abug | Done | View a list of the site's opinion poll questions | 2 | Bugs
38 | Test default image functionality on Heroku site (create article) | Done | All User Stories | All | Testing
39 | Check if can get a message for comments being added | Done | Comment on an article | 1 | Features
40 | Dev server | Done | Comment on an article | 1 | Features
41 | Heroku | Done | Comment on an article | 1 | Features
42 | Add post_list view test to automated testing tables & update coverage | Done | View articles listing | 1 | Testing
43 | Rename project folder to Django blog | Done | All User Stories | All | Renaming
44 | Add comment message to javascript testing section & features section | Done | Approve comments | 1 | Features
45 | Add “real world use case” to intro – help people w/Django | Done | All User Stories | All | UX
46 | Replace Django images with pexels (will be good for credits + remove any potential issues) | Done | Article Organisation | 1 | Content
47 | Update comments ERD – articles instead of posts | Done | View article comments | 1 | UX
48 | Favicon bug – would only show on home page – wrong file link (/) | Done | View article comments | 1 | Bugs
49 | Favicon bug – would only show on dev server (needed to use cloudinary) | Done | View article comments | 1 | Bugs
50 | Find out how to do testing coverage? | Done | All User Stories | All | Testing
51 | Recheck testing post model rename | Done | All User Stories | All | Testing
52 | Add authentication & authorisation to features | Done | All User Stories | All | Features
53 | Check for inline stylings & remove any (2x on article_detail.html) | Done | Add a like to an article | 1 | UX
54 | Make Comment Icons green instead of red/black | Done | Add a like to an article | 1 | UX
55 | Possibly have Masthead uniform in color (not different shades of green), or even remove the triangular line | Done | Add a like to an article | 1 | UX
56 | Change like icon to thumbs-up | Done | Add a like to an article | 1 | UX
57 | Add banner to articles page, similar to polls & home for consistency | Done | Add a like to an article | 1 | UX
58 | Change author to uppercase on article detail page e.g. dan is lowercase beside masthead | Done | Add a like to an article | 1 | UX
59 | Commenting bug – on page refresh the comment resubmits – how to avoid? | Done | View article comments | 1 | Bugs
60 | Add solution to bugs in readme + Kanban | Done | View article comments | 1 | Bugs
61 | Add solution to Javascript testing | Done | View article comments | 1 | Testing
62 | Close & resolve Bug#9 | Done | Article Management | 1 | Bugs
63 | Articles: | Done | Article Management | 1 | Content
64 | 6x total – one per day | Done | Article Management | 1 | Content
65 | What is Django | Done | Article Management | 1 | Content
66 | Who Uses Django | Done | Article Management | 1 | Content
67 | Why Use Django | Done | Article Management | 1 | Content
68 | How does Django work | Done | Article Management | 1 | Content
69 | Approaches to learning Django | Done | Article Management | 1 | Content
70 | Useful Django resources | Done | Article Management | 1 | Content
71 | Add 2x pictures to each article | Done | Article Management | 1 | Content
72 | Add – if you liked this article, why not leave a thumbs-up in the section below | Done | Article Management | 1 | Content
73 | See if can make page refresh on same place it was clicked after clicking like icon | Done | Like / Unlike | 1 | Features
74 | See if can get Javascript extracted from html over to base.js | Done | Like / Unlike | 1 | Features
75 | Page scroll on refresh | Done | Like / Unlike | 1 | Features
76 | Add bug to readme (5 mins) | Done | Like / Unlike | 1 | Bugs
77 | Add bug to Kanban (5 mins) | Done | Like / Unlike | 1 | Bugs
78 | Add JS test to testing (5 mins) | Done | Like / Unlike | 1 | Testing
79 | Get comments totals added to article titles | Done | View article comments | 1 | Features
80 | Get date formats changed to take up less space (responsiveness) | Done | View article comments | 1 | Features
81 | Testing: | Done | All User Stories | All | Testing
82 | Accessibility testing still needs a bit of work | Done | All User Stories | All | Testing
83 | Browser compatibility needs a bit of work also | Done | All User Stories | All | Testing
84 | Also re-do HTML validation | Done | All User Stories | All | Testing
85 | CSS Validation | Done | All User Stories | All | Testing
86 | Javascript Validation | Done | All User Stories | All | Testing
87 | And redo PEP8 validation | Done | All User Stories | All | Testing
88 | Uncomment email verification in settings.py | Done | All User Stories | All | Features
89 | Features | Done | View a list of the opinion poll question answer choices | 2 | Features
90 | Go through & update all screenshots | Done | View a list of the opinion poll question answer choices | 2 | Features
91 | Adds: | Done | View a list of the opinion poll question answer choices | 2 | Features
92 | Likes & Comments on article titles | Done | View Likes | 1 | Features
93 | Masthead changes | Done | View a list of the opinion poll question answer choices | 2 | Features
94 | Final tidy up: | Done | All User Stories | All | Readme update
95 | Update all screenshots with current UX rev | Done | All User Stories | All | Readme update
96 | Full & Final spellchecking | Done | All User Stories | All | Readme update
97 | Code comments | Done | All User Stories | All | Code validation
98 | Add docstrings to python classes & functions | Done | All User Stories | All | Code validation
99 | Scrub credits – add fifth example from Ken + Django Girls Forum question | Done | All User Stories | All | Credits
100 | Add `poll` folder in backticks in credits code section | Done | View a list of the site's opinion poll questions | 2 | Credits